## general_report
CANDIDATE FOR THE NEXT RELEASE?
New York Magazine
Displaying 155 issues at 16/Aug/12 10:58 PM.
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Component/s | Fix Version/s
Bug | CUT-986 | Desktop and iPad: Videos in articles are not playing in Safari and IE | Randi Eichenbaum | Randi Eichenbaum | Blocker | Resolved | Resolved | 2012-08-11 22:15 | 2012-08-16 19:47 | Articles | Highest Priority Post Launch Bugs | YES
Bug | CUT-977 | Runway Opener on Mobile - Most Popular carousel styling incorrect | Kristen Dudish | Kristen Dudish | Critical | Resolved | Resolved | 2012-08-11 20:41 | 2012-08-16 17:29 | Runway Show Opener & Finder | Fashion Week Bug List | YES
Bug | CUT-345 | Splash Pages: Feed: Name of feed (e.g. "Beauty Newsfeed") and black horizontal line not appearing. | Miwa Yagi | Alicia Brooks | Critical | Resolved | Resolved | 2012-07-11 15:56 | 2012-08-16 13:53 | Splash Pages - All | Highest Priority Post Launch Bugs | YES
Bug | CUT-978 | Runway Lede - Season displaying as one word "FALL2012COUTURE" | Kristen Dudish | Kristen Dudish | Critical | Resolved | Fixed | 2012-08-11 20:43 | 2012-08-16 13:20 | Splash Pages - Runway | Fashion Week Bug List | YES
Bug | CUT-886 | Can't create shows for new labels | Randi Eichenbaum | Randi Eichenbaum | Blocker | Resolved | Fixed | 2012-08-09 18:37 | 2012-08-16 13:15 | Show Builder | Fashion Week Bug List | YES
Bug | CUT-1064 | need to adjust ad height on goods section page | Kevin Barnett | Randi Eichenbaum | Blocker | Resolved | None | 2012-08-14 10:45 | 2012-08-16 13:11 | Splash Pages - Goods | Highest Priority Post Launch Bugs | IS KEVIN SAYING NOTHING DONE?
Task | CUT-1120 | errorneous slide should not kill entire slideshow json | Sam Lee | Sam Lee | Critical | Resolved | Fixed | 2012-08-16 11:09 | 2012-08-16 12:25 |  |  | YES
Bug | CUT-1088 | Love and war splash page - bar above news feed slices through top story in feed | Nicole Smith | Nicole Smith | Critical | Resolved | Resolved | 2012-08-14 15:39 | 2012-08-16 09:41 | Splash Pages - All | Highest Priority Post Launch Bugs | YES
Bug | CUT-76 | Have to refresh the Edit Show Page in the Runway Show Builder page to recognize images | Randi Eichenbaum | Randi Eichenbaum | Major | Resolved | Fixed | 2012-04-09 12:38 | 2012-08-15 17:30 | Show Builder | Fashion Week Bug List | YES
Bug | CUT-1056 | Large Vertical - Increase height of visible article text area | Kristen Dudish | Kristen Dudish | Major | Resolved | Resolved | 2012-08-13 18:23 | 2012-08-15 16:44 | Articles | Highest Priority Post Launch Bugs | YES
Bug | CUT-721 | ***This will be out tonight*** Premium Slideshows: Adjust caption text and photo credit size and line height | Kristen Dudish | Kristen Dudish | Major | Resolved | Resolved | 2012-08-02 15:48 | 2012-08-15 16:42 | Slideshow UX | Fashion Week Bug List | YES
Bug | CUT-1037 | Slideshow captions not displaying on IE8 | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Resolved | 2012-08-13 13:31 | 2012-08-15 16:34 | Slideshow UX | Highest Priority Post Launch Bugs | YES
Bug | CUT-1021 | Manual Homepage Lede Positioning not working | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Fixed | 2012-08-13 11:21 | 2012-08-15 14:44 | Home Page & Modules | Highest Priority Post Launch Bugs | YES
Bug | CUT-51 | Unable to add a model that is not yet in our database. | Randi Eichenbaum | Randi Eichenbaum | Minor | Resolved | None | 2012-01-20 18:41 | 2012-08-15 13:44 | Image Tagger |  | NO
Bug | CUT-1092 | Runway Slideshows: Top of heads are getting cut off in thumbnails | Randi Eichenbaum | Randi Eichenbaum | Major | Resolved | Won't Fix | 2012-08-14 16:14 | 2012-08-15 11:31 | Slideshow UX | Fashion Week Bug List | NO. SHOULD THIS BE REOPENED?
Bug | CUT-1060 | image management akamai cache invalidation stopped functioning | Sam Lee | Sam Lee | Blocker | Resolved | Fixed | 2012-08-14 10:01 | 2012-08-14 18:34 |  | Highest Priority Post Launch Bugs
Bug | CUT-37 | When multiple models are added to image tagger image, only the final person is displayed as the "model" in the slideshow preview | Randi Eichenbaum | Randi Eichenbaum | Minor | Resolved | None | 2012-01-09 15:29 | 2012-08-14 17:26 | Image Tagger
New Feature | CUT-43 | "Designer Photo" feature questions | Randi Eichenbaum | Randi Eichenbaum | Minor | Resolved | None | 2012-01-09 15:46 | 2012-08-14 17:25 | Image Tagger, Look Finder
New Feature | CUT-39 | Add ability to have multiple of the same clothing type (i.e. 2 tops, or 2 jewelries) | Randi Eichenbaum | Randi Eichenbaum | Minor | Resolved | None | 2012-01-09 15:33 | 2012-08-14 17:24 | Image Tagger
Improvement | CUT-35 | Model/person tagging is not easy to use due to sheer number of models to choose from through autocomplete | Randi Eichenbaum | Randi Eichenbaum | Minor | Resolved | None | 2012-01-09 15:22 | 2012-08-14 17:22 | Image Tagger
Bug | CUT-1078 | When closing out of a slideshow, difficulty with scrolling down on the article page. | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Cannot Reproduce | 2012-08-14 11:56 | 2012-08-14 16:53 | Slideshow UX | Highest Priority Post Launch Bugs
Bug | CUT-540 | Internal Server Error on article (STG) | Unassigned | Nicole Smith | Critical | Resolved | None | 2012-07-26 14:09 | 2012-08-14 16:29 | Articles
Bug | CUT-587 | ON STG: Articles: Copied text is not formatting correctly. | Randi Eichenbaum | Randi Eichenbaum | Major | Resolved | None | 2012-07-27 13:44 | 2012-08-14 16:28 | Articles
Bug | CUT-401 | ON STG AND EC2: The " View Show Opener & Slideshow" link listed under the Collection and all other related galleries is linking to the wrong thing/showing outdated text. | Randi Eichenbaum | Randi Eichenbaum | Major | Resolved | None | 2012-07-16 12:06 | 2012-08-14 16:28 | Show Builder
Bug | CUT-395 | ON STG AND EC2: Link to the Image Tagging Tool for Related Galleries does not work. | Randi Eichenbaum | Randi Eichenbaum | Major | Resolved | None | 2012-07-15 17:28 | 2012-08-14 16:27 | Show Builder
Bug | CUT-680 | On STG: Splash Pages: Section Lede: If you refresh the page before activating, you will lose the manual entries you've entered into the lede component. | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | None | 2012-08-01 11:11 | 2012-08-14 16:26 | Splash Pages - All
Bug | CUT-1032 | Need to restore workflow functionality for adding Related Stories in articles | Randi Eichenbaum | Randi Eichenbaum | Major | Resolved | Cannot Reproduce | 2012-08-13 12:26 | 2012-08-14 16:18 | Articles | Highest Priority Post Launch Bugs
Bug | CUT-1040 | lede image runs of left side of page on ipad | Nicole Smith | Nicole Smith | Critical | Resolved | Resolved | 2012-08-13 15:28 | 2012-08-14 15:01 | Runway Show Opener & Finder | Highest Priority Post Launch Bugs
Bug | CUT-1079 | Homepage loading in very broken in Chrome and Firefox | Kelly Maloni | Kristen Dudish | Blocker | Resolved | Fixed | 2012-08-14 12:10 | 2012-08-14 14:46 | Home Page & Modules | Highest Priority Post Launch Bugs
Bug | CUT-1076 | Capitalization rules are not being applied in the feed. | Randi Eichenbaum | Randi Eichenbaum | Major | Resolved | Fixed | 2012-08-14 11:51 | 2012-08-14 14:16 | Home Page & Modules, Splash Pages - All | Highest Priority Post Launch Bugs
Bug | CUT-927 | "Runway Video" link appears even if the show doesn't have a video. | Georges Labreche | Georges Labreche | Critical | Resolved | Fixed | 2012-08-11 17:14 | 2012-08-14 14:02 | Runway Show Opener & Finder | Highest Priority Post Launch Bugs
Sub-task | CUT-636 | CUT-635 PRE-LAUNCH: Performance Analysis | Larry Chevres | Larry Chevres | Major | Resolved | Resolved | 2012-07-30 17:35 | 2012-08-14 13:07 |  | Pre-Launch Tasks
Sub-task | CUT-638 | CUT-635 PRE-LAUNCH: Runway Shows | Larry Chevres | Larry Chevres | Major | Resolved | Resolved | 2012-07-30 17:40 | 2012-08-14 13:06 |  | Pre-Launch Tasks
Sub-task | CUT-642 | CUT-635 PRE-LAUNCH: Varnish: Fine Tune Rules | Larry Chevres | Larry Chevres | Major | Resolved | Resolved | 2012-07-30 17:48 | 2012-08-14 13:06 |  | Pre-Launch Tasks
Sub-task | CUT-640 | CUT-635 PRE-LAUNCH: Warm Akamai Cache for Runway | Larry Chevres | Larry Chevres | Major | Resolved | Resolved | 2012-07-30 17:42 | 2012-08-14 13:06 |  | Pre-Launch Tasks
Sub-task | CUT-637 | CUT-635 PRE-LAUNCH: CQ Error Log Analysis | Larry Chevres | Larry Chevres | Major | Resolved | Resolved | 2012-07-30 17:36 | 2012-08-14 13:06 |  | Pre-Launch Tasks
Story | CUT-635 | PRE-LAUNCH: Performance Related Tasks | Larry Chevres | Larry Chevres | Critical | Resolved | Resolved | 2012-07-30 17:33 | 2012-08-14 13:05 |  | Pre-Launch Tasks
Bug | CUT-1041 | Users accidentally closing the whole slideshow while trying to continue past the ad in a slideshow | Dave Epstein | Dave Epstein | Critical | Resolved | Fixed | 2012-08-13 15:33 | 2012-08-14 12:04 | Slideshow UX
Bug | CUT-1019 | ***This will be out tonight*** Mobile - Large vertical template on mobile has spacing issues between hed and article content and body text size is too small | Kristen Dudish | Kristen Dudish | Major | Resolved | Resolved | 2012-08-13 11:05 | 2012-08-13 19:13 | Articles | Fashion Week Bug List
Bug | CUT-929 | apps/nymag/config needs to be updated with a value for HostConfig's "cutHost.name" property | Georges Labreche | Georges Labreche | Critical | Resolved | Fixed | 2012-08-11 17:26 | 2012-08-13 18:03 | Splash Pages - Runway | Highest Priority Post Launch Bugs
Bug | CUT-971 | Image on post is displaying enlarge and zoom controls but larger image doesn't display upon enlarge. | Randi Eichenbaum | Randi Eichenbaum | Blocker | Resolved | Resolved | 2012-08-11 20:10 | 2012-08-13 17:20 | Articles | Highest Priority Post Launch Bugs
Bug | CUT-1052 | enlarge this displays blank if original image is chosen by javascript | Kelly Maloni | Sam Lee | Critical | Resolved | Fixed | 2012-08-13 16:52 | 2012-08-13 17:18 |  | Highest Priority Post Launch Bugs
Bug | CUT-908 | FIXED - Lede articles link to different article (wrong url) on splash pages | Nicole Smith | Nicole Smith | Critical | Resolved | Resolved | 2012-08-10 14:50 | 2012-08-13 10:59 | Articles
Story | CUT-597 | LAUNCH RELATED TASKS | Trista Spidaletto | Trista Spidaletto | Critical | Resolved | Closed | 2012-07-27 17:13 | 2012-08-13 10:57 |  | Launch Tasks
Task | CUT-943 | add cpu and ram on author | Sam Lee | Sam Lee | Blocker | Resolved | Fixed | 2012-08-11 17:59 | 2012-08-11 20:56 |  | Highest Priority Post Launch Bugs
Sub-task | CUT-799 | CUT-597 Push text files to Prod (for the links in the NYMag Fashion Subnav & NYMag CSS) | Kelly Maloni | Kelly Maloni | Critical | Resolved | Fixed | 2012-08-07 11:59 | 2012-08-11 19:50 | NYMag Changes | Launch Tasks
Bug | CUT-899 | IE8: 3 or 4 banner ads are appearing at the bottom of runway show openers | Kelly Maloni | Kelly Maloni | Blocker | Resolved | Fixed | 2012-08-10 00:28 | 2012-08-11 19:23 | Ads, Runway Show Opener & Finder | Sprint 83
Bug | CUT-865 | FIXED*** Lede divider can go on top of the first feed post | Dave Epstein | Dave Epstein | Critical | Resolved | Resolved | 2012-08-08 14:21 | 2012-08-11 19:23 | Splash Pages - All
Bug | CUT-824 | FIXED*** Section Page Feeds - first post in feed is overlapping border above it | Kristen Dudish | Kristen Dudish | Critical | Resolved | Resolved | 2012-08-07 17:35 | 2012-08-11 19:22 | Splash Pages - All | Sprint 83
Bug | CUT-894 | FIXED: IE8: Look Book carousels are not working. Need to be hid or fixed | Kelly Maloni | Kelly Maloni | Critical | Resolved | Fixed | 2012-08-10 00:10 | 2012-08-11 18:59 | Home Page & Modules
Sub-task | CUT-593 | CUT-597 LAUNCH TASK: Search app udate for thecut launch | Sam Lee | Sam Lee | Critical | Resolved | Fixed | 2012-07-27 16:34 | 2012-08-11 18:21 |  | Launch Tasks
Bug | CUT-892 | FIXED *** IE8: Cut Logo is not readable in nav bar | Kelly Maloni | Kelly Maloni | Blocker | Resolved | Resolved | 2012-08-10 00:04 | 2012-08-11 17:47 | Cut Navigation | Sprint 83
Bug | CUT-912 | Begin Slideshow button doesn't open slideshow in IE | Unassigned | Ilya Gulko | Critical | Resolved | Fixed | 2012-08-10 19:30 | 2012-08-10 19:53 | Slideshow UX
Bug | CUT-903 | FIXED: Add slideshow tracking code to slideshows | Kelly Maloni | Kelly Maloni | Blocker | Resolved | Fixed | 2012-08-10 00:41 | 2012-08-10 19:17 | Slideshow UX | Sprint 83
Bug | CUT-882 | Lede - Mobile - Headline size adjustments | Kristen Dudish | Kristen Dudish | Major | Resolved | Fixed | 2012-08-09 15:08 | 2012-08-10 18:56 | Home Page & Modules
Bug | CUT-697 | Footer - CSS adjustments | Kristen Dudish | Kristen Dudish | Minor | Resolved | Fixed | 2012-08-01 17:14 | 2012-08-10 17:51 | Cut Navigation
Bug | CUT-826 | Next/Previous article buttons are partially or entirely cut off when viewport is <1150px | Ilya Gulko | Ilya Gulko | Major | Resolved | Won't Fix | 2012-08-07 17:38 | 2012-08-10 17:35 | Articles, Cut Navigation, Slideshow UX
Bug | CUT-838 | Mobile - CSS adjustments for View Slideshow buttons | Kristen Dudish | Kristen Dudish | Major | Resolved | Won't Fix | 2012-08-07 18:21 | 2012-08-10 17:27 | Splash Pages - News Section
Bug | CUT-842 | Tablet - CSS adjustments for View Slideshow buttons | Kristen Dudish | Kristen Dudish | Major | Resolved | Fixed | 2012-08-07 18:35 | 2012-08-10 17:24 | Splash Pages - News Section
Bug | CUT-900 | IE8: Slideshow data and navigation are covered by giant ads | Kelly Maloni | Kelly Maloni | Blocker | Resolved | Fixed | 2012-08-10 00:31 | 2012-08-10 17:05 | Ads, Slideshow UX | Sprint 83
Bug | CUT-618 | Bottom 728x90 ads should be lazy loaded | Kelly Maloni | Kelly Maloni | Critical | Resolved | Fixed | 2012-07-30 01:40 | 2012-08-10 16:35 | Ads
Bug | CUT-909 | FIXED Article Thumbnails are appearing over the article body copy | Dave Epstein | Dave Epstein | Critical | Resolved | Resolved | 2012-08-10 15:36 | 2012-08-10 16:27 | Articles
Bug | CUT-406 | Thumbnails for articles in news feed are not styled correctly | Unassigned | Nicole Smith | Major | Resolved | Fixed | 2012-07-16 12:27 | 2012-08-10 16:26 | Splash Pages - News Section
Bug | CUT-891 | FIXED: The footer should have four mobile ad sizes in the flex tag | Kelly Maloni | Kelly Maloni | Blocker | Resolved | Fixed | 2012-08-10 00:02 | 2012-08-10 16:26 | Ads | Sprint 83
Bug | CUT-862 | Image is appearing over text in an article | Dave Epstein | Dave Epstein | Critical | Resolved | Resolved | 2012-08-08 12:16 | 2012-08-10 16:24 | Articles
Bug | CUT-655 | Newsfeed: Adjust spacing below blogvertorial ad in feed and add dotted rule | Kristen Dudish | Kristen Dudish | Major | Resolved | Fixed | 2012-07-31 12:04 | 2012-08-10 16:23 | Ads, Splash Pages - News Section
Bug | CUT-895 | FIXED PENDING MERGE: IE8: Homepage: Giant Image isn't displaying in bottom unit | Kelly Maloni | Kelly Maloni | Blocker | Resolved | Resolved | 2012-08-10 00:13 | 2012-08-10 14:30 | Home Page & Modules | Sprint 83
Bug | CUT-896 | IE8: Articles: "Show More" not working in right column news feed unit | Matt Ruby | Kelly Maloni | Major | Resolved | Resolved | 2012-08-10 00:18 | 2012-08-10 14:29 | Articles
Bug | CUT-687 | Typing in the search box doesn't clear the word 'Search' | Dave Epstein | Dave Epstein | Critical | Resolved | Resolved | 2012-08-01 12:46 | 2012-08-10 13:42 | Cut Navigation
Bug | CUT-907 | iPhone: Interview Header is obscured by the image | Dave Epstein | Dave Epstein | Critical | Resolved | Fixed | 2012-08-10 11:36 | 2012-08-10 12:39 | Home Page & Modules
Bug | CUT-530 | Universal Nav: The Magazine links are not working | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Fixed | 2012-07-25 17:07 | 2012-08-10 11:54 | Cut Navigation
Bug | CUT-851 | FIXED: Can not add primary image or slideshow component to Large Vertical template articles [Fix checked in pending merge] | Randi Eichenbaum | Randi Eichenbaum | Blocker | Resolved | Fixed | 2012-08-07 20:11 | 2012-08-10 10:57 | Articles | Sprint 83
Bug | CUT-507 | On both homepage and internal nav, 'The Magazine' dropdown is very jumpy | Randi Eichenbaum | Randi Eichenbaum | Major | Resolved | Fixed | 2012-07-24 19:54 | 2012-08-09 19:22 | Cut Navigation
Bug | CUT-880 | Enlarge This/Zoom not appearing on 4x vertical images on EC2 | Randi Eichenbaum | Nicole Smith | Critical | Resolved | Won't Fix | 2012-08-09 11:37 | 2012-08-09 19:21 | Dashboard | Sprint 83
Bug | CUT-766 | Ads on Goods section not implemented correctly | Kelly Maloni | Kelly Maloni | Critical | Resolved | Fixed | 2012-08-06 00:19 | 2012-08-09 18:47 | Ads, Splash Pages - Goods | Sprint 83
Bug | CUT-709 | Standard Slideshow: Revise link color and hover in caption text | Kristen Dudish | Kristen Dudish | Major | Resolved | Resolved | 2012-08-02 11:44 | 2012-08-09 18:45 | Slideshow UX
Bug | CUT-711 | Standard Slideshow: Revise color of back to article link text and add hover state | Steve Motzenbecker | Kristen Dudish | Major | Resolved | Closed | 2012-08-02 11:53 | 2012-08-09 18:31 | Slideshow UX
Bug | CUT-831 | Chrome - Dropdown arrow next to FASHIONS inconsistently shifts to the left, crashing into FASHIONS text | Kristen Dudish | Kristen Dudish | Major | Resolved | Fixed | 2012-08-07 17:48 | 2012-08-09 17:47 | Cut Navigation
Bug | CUT-491 | Latest Headlines /Top Stories/ News Feed text is cut off on left hand side of tablet/mobile sized viewport | Steve Motzenbecker | Nicole Smith | Major | Resolved | Closed | 2012-07-24 11:43 | 2012-08-09 17:36 | Articles
Bug | CUT-431 | Opener: View the Collection Button and Link hovers/transitions | Steve Motzenbecker | Kristen Dudish | Major | Resolved | Closed | 2012-07-18 12:26 | 2012-08-09 17:36 | Runway Show Opener & Finder
Bug | CUT-427 | Slideshow button styling and hover transitions | Kristen Dudish | Kristen Dudish | Minor | Resolved | Fixed | 2012-07-18 12:12 | 2012-08-09 17:28 | Articles
Bug | CUT-379 | Tablet: spacing issues on No Image templates | Kristen Dudish | Kristen Dudish | Major | Resolved | Fixed | 2012-07-13 11:15 | 2012-08-09 17:08 | Articles
Bug | CUT-375 | Tablet: spacing issues on Medium Horizontal template | Kristen Dudish | Kristen Dudish | Major | Resolved | Fixed | 2012-07-12 18:07 | 2012-08-09 17:08 | Articles
Bug | CUT-377 | Tablet: spacing issues on Medium Vertical templates | Kristen Dudish | Kristen Dudish | Major | Resolved | Fixed | 2012-07-13 10:36 | 2012-08-09 17:07 | Articles
Bug | CUT-378 | Tablet: spacing issues on Thumbnail templates | Kristen Dudish | Kristen Dudish | Major | Resolved | Fixed | 2012-07-13 10:58 | 2012-08-09 17:07 | Articles
Bug | CUT-443 | Pictures Module: Exclude posts tagged "goods" or "look book" | Kelly Maloni | Kelly Maloni | Critical | Resolved | Fixed | 2012-07-18 22:31 | 2012-08-09 17:01 | Home Page & Modules | Sprint 83
Bug | CUT-850 | Image Tagger Not loading non-runway images | Kelly Maloni | Kelly Maloni | Critical | Resolved | Fixed | 2012-08-07 19:44 | 2012-08-09 16:29 | Image Tagger | Sprint 83
Bug | CUT-393 | Slideshows (all types) are only pulling from the "Source" field (should be Courtesy + Source) -- Jed Egan actual reporter of bug | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Fixed | 2012-07-13 17:38 | 2012-08-09 16:27 | Slideshow UX | Sprint 83
Bug | CUT-746 | Unable to launch slideshows from articles in IE9 | Kristen Dudish | Kristen Dudish | Blocker | Resolved | Fixed | 2012-08-03 15:33 | 2012-08-09 16:24 | Articles | Sprint 83
Bug | CUT-698 | Look Books module: Mobile -- Carousel not working | Kristen Dudish | Kristen Dudish | Critical | Resolved | Fixed | 2012-08-01 17:22 | 2012-08-09 16:23 | Home Page & Modules | Sprint 83
Bug | CUT-758 | Correct photo credits are not displaying on slideshows when added to the slideshow tool. | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Won't Fix | 2012-08-03 22:29 | 2012-08-09 16:22 | Slideshow Tool, Slideshow UX | Sprint 83
Bug | CUT-871 | Large Vertical - Firefox -Text column breaking to right side and overlapping ad unit | Kristen Dudish | Kristen Dudish | Critical | Resolved | Fixed | 2012-08-08 17:19 | 2012-08-09 16:21 | Articles | Sprint 83
Bug | CUT-614 | On STG: Drop Caps appearing in block quotes when they shouldn't be. | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Fixed | 2012-07-29 12:38 | 2012-08-09 16:20 | Articles | Sprint 83
Bug | CUT-175 | Runway Splash: Runway Splash Lede: Silo image not aligned to right edge | Ilya Gulko | Ilya Gulko | Major | Resolved | Resolved | 2012-05-24 18:15 | 2012-08-09 16:20 | Runway Show Opener & Finder
Bug | CUT-811 | Homepage lede module rotates too quickly (very, very quickly) through all the ledes | Kelly Maloni | Kelly Maloni | Critical | Resolved | Resolved | 2012-08-07 13:49 | 2012-08-09 16:19 | Home Page & Modules | Sprint 83
Bug | CUT-699 | Runway Lede not displaying properly on mobile -- desktop layout being squished into mobile viewport | Kristen Dudish | Kristen Dudish | Critical | Resolved | Resolved | 2012-08-01 17:29 | 2012-08-09 16:19 | Splash Pages - Runway | Sprint 83
Bug | CUT-808 | Homepage lede on IE8 and IE9 is a disaster | Kelly Maloni | Kelly Maloni | Blocker | Resolved | Resolved | 2012-08-07 13:44 | 2012-08-09 16:16 | Home Page & Modules | Sprint 83
Bug | CUT-859 | Can't close zoomed in pic in slideshow | Dave Epstein | Dave Epstein | Critical | Resolved | Fixed | 2012-08-08 11:30 | 2012-08-09 16:08 | Slideshow UX | Sprint 83
Bug | CUT-867 | Magnifying lens appears in thumbnail view | Dave Epstein | Dave Epstein | Critical | Resolved | Fixed | 2012-08-08 14:38 | 2012-08-09 16:08 | Slideshow UX
Bug | CUT-873 | Clicking on Load More in the feed displays posts, but NO images. | Kristen Dudish | Kristen Dudish | Critical | Resolved | Fixed | 2012-08-08 19:47 | 2012-08-09 16:05 | Splash Pages - All | Sprint 83
Bug | CUT-800 | Wrong Facebook App ID in Meta Data on Homepage and Section Pages / Missing From Articles | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Won't Fix | 2012-08-07 12:11 | 2012-08-09 15:49 | General Site Issues | Sprint 83
Bug | CUT-436 | Author links on Large Vertical templates: add underline and hover transition | Kristen Dudish | Kristen Dudish | Minor | Resolved | Cannot Reproduce | 2012-07-18 16:16 | 2012-08-09 14:53 | Articles
Bug | CUT-320 | "Source" links not styled properly | Kristen Dudish | Kristen Dudish | Minor | Resolved | Fixed | 2012-07-10 14:14 | 2012-08-09 14:38 | Articles
Bug | CUT-362 | Mobile: Increase font size of body text on articles with vertical image | Kristen Dudish | Kristen Dudish | Minor | Resolved | Won't Fix | 2012-07-12 15:50 | 2012-08-09 14:32 | Articles
Bug | CUT-358 | Mobile: Hed positioning and line height | Kristen Dudish | Kristen Dudish | Minor | Resolved | Fixed | 2012-07-12 15:33 | 2012-08-09 14:25 | Articles |  | need iPhone
Bug | CUT-817 | iPhone: the goods page dots are over the image and are hard to see | Dave Epstein | Dave Epstein | Critical | Resolved | Resolved | 2012-08-07 15:08 | 2012-08-09 14:18 | Home Page & Modules |  | need iPhone
Bug | CUT-849 | Site is referencing outdated Twitter and Facebook pages for TheCut | Kevin Barnett | Kelly Maloni | Blocker | Resolved | Fixed | 2012-08-07 19:34 | 2012-08-09 11:44 | Articles | Sprint 83
Bug | CUT-877 | Unable to delete tags | Kelly Maloni | Kelly Maloni | Critical | Resolved | Fixed | 2012-08-09 01:54 | 2012-08-09 11:21 | Articles | Sprint 83 | Needs to be done on author
Bug | CUT-848 | Mobile - Share tools - Should display at bottom of ALL articles regardless of text length, and hide all BUT Facebook, Twitter and Email | Kristen Dudish | Kristen Dudish | Critical | Resolved | Won't Fix | 2012-08-07 19:21 | 2012-08-09 11:20 | Articles |  | Sharetools hidden
Bug | CUT-861 | Feed doesn't have enough space between posts | Unassigned | Dave Epstein | Critical | Resolved | Closed | 2012-08-08 11:59 | 2012-08-08 21:17 | General Site Issues
Bug | CUT-772 | Goods Lede - Positioning of image and headline is incorrect | Kristen Dudish | Kristen Dudish | Critical | Resolved | Resolved | 2012-08-06 12:22 | 2012-08-08 19:30 | Splash Pages - Goods |  | Image on prod still looks like it's too high up into the Goods header
Bug | CUT-666 | Loading or resizing the home page results in several image requests that 404 | Kelly Maloni | Ilya Gulko | Major | Resolved | Fixed | 2012-07-31 15:44 | 2012-08-08 19:18 | Home Page & Modules | Sprint 83
Bug | CUT-684 | Fashion Shows Module: Tablet -- CSS adjustments | Kristen Dudish | Kristen Dudish | Critical | Resolved | Fixed | 2012-08-01 12:15 | 2012-08-08 16:37 | Home Page & Modules | Fashion Week Bug List
Bug | CUT-376 | Mobile/Tablet: Top slideshow buttons for thumbnail, 190, and medium vertical (mobile only) should be positioned directly below image, not overlaying | Kristen Dudish | Kristen Dudish | Major | Resolved | Resolved | 2012-07-12 18:33 | 2012-08-08 15:52 | Articles |  | mobile/tablet needed
Bug | CUT-846 | Slideshows won't save if Graphic Image URL field is populated. | Georges Labreche | Randi Eichenbaum | Critical | Resolved | Fixed | 2012-08-07 19:18 | 2012-08-08 15:43 | Slideshow Tool | Sprint 83 | Need clarification from Georges, not sure what the bug is
Task | CUT-801 | Remove the Section Page options in the promotion area for Fashion Trends and Fashion Shows | Kelly Maloni | Kelly Maloni | Minor | Resolved | Fixed | 2012-08-07 12:33 | 2012-08-08 15:43 | Articles
Bug | CUT-802 | The dialog box for Enlarge This is unreadable | Kelly Maloni | Kelly Maloni | Major | Resolved | Fixed | 2012-08-07 12:38 | 2012-08-08 15:31 | Articles | Sprint 83
Bug | CUT-374 | Tablet: font sizes for all article templates | Kristen Dudish | Kristen Dudish | Major | Resolved | Fixed | 2012-07-12 17:42 | 2012-08-08 13:22 | Articles |  | Need tablet
Sub-task | CUT-794 | CUT-597 Update the links in the NYMag Fashion Subnav | Kelly Maloni | Kelly Maloni | Critical | Resolved | Fixed | 2012-08-07 01:31 | 2012-08-08 12:43 | NYMag Changes | Launch Tasks
Bug | CUT-581 | Unable to add secondary image because component box is being blocked with Commenting overlay. | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Cannot Reproduce | 2012-07-27 13:03 | 2012-08-08 12:40 | Articles |  | Need to alter prod articles to confirm.
Bug | CUT-815 | Single Related Story Module (earlier) images are distorted/stretched | Kelly Maloni | Kelly Maloni | Critical | Resolved | Cannot Reproduce | 2012-08-07 14:04 | 2012-08-07 20:09 | Articles | Sprint 83
Bug | CUT-787 | Chrome Browser bugs for slideshow experience | Steve Motzenbecker | Randi Eichenbaum | Blocker | Resolved | Fixed | 2012-08-06 16:36 | 2012-08-07 18:37 | Slideshow UX | Sprint 83
Bug | CUT-664 | iPhone: View Slideshow text goes off viewport | Dave Epstein | Dave Epstein | Critical | Resolved | Resolved | 2012-07-31 15:35 | 2012-08-07 13:58 | Articles |  | requires iphone
Bug | CUT-769 | Most Popular Module: CSS styling adjustments | Kristen Dudish | Kristen Dudish | Critical | Resolved | Fixed | 2012-08-06 11:13 | 2012-08-07 13:11 | Home Page & Modules
Bug | CUT-744 | IE8 & IE9 -- Images missing all over homepage and section pages | Kristen Dudish | Kristen Dudish | Critical | Resolved | Fixed | 2012-08-03 15:25 | 2012-08-07 13:11 | Home Page & Modules, Splash Pages - All | Sprint 83 | Not yet fixed. Similar to IE9 'backward compatibility' bug
Bug | CUT-518 | Right column Top Stories & Latest Headlines module: Styling | Steve Motzenbecker | Kristen Dudish | Critical | Resolved | Resolved | 2012-07-25 10:21 | 2012-08-06 15:16 | Articles | Sprint 83
Bug | CUT-432 | Show Opener Pages: Long Critical Reactions is running into the Top Shows Carousel | Randi Eichenbaum | Randi Eichenbaum | Major | Resolved | Resolved | 2012-07-18 12:30 | 2012-08-06 14:15 | Runway Show Opener & Finder |  | Critical reaction not implemented on prod
Bug | CUT-247 | Refreshing a slide from a connection results in an error. | Nano Anderson | Randi Eichenbaum | Critical | Resolved | Cannot Reproduce | 2012-06-13 18:11 | 2012-08-06 11:59 | Slideshow UX
Bug | CUT-673 | nav bar 'section' dropdown does not consistently work on mobile | Nicole Smith | Nicole Smith | Major | Resolved | Fixed | 2012-07-31 16:28 | 2012-08-05 22:40 | Splash Pages - All |  | requires iPhone
Bug | CUT-311 | Comment sorting controls are missing | Ilya Gulko | Ilya Gulko | Critical | Resolved | Closed | 2012-07-08 13:27 | 2012-08-05 22:27 | Articles
Bug | CUT-700 | News feed articles do not display on tablet-sized viewport (EC2) | Nicole Smith | Nicole Smith | Critical | Resolved | Resolved | 2012-08-01 18:08 | 2012-08-05 20:41 | Home Page & Modules |  | Requires tablet
Bug | CUT-670 | Ad appears on tablet layout when it shouldn't | Ilya Gulko | Ilya Gulko | Critical | Resolved | Resolved | 2012-07-31 15:54 | 2012-08-05 20:40 | Home Page & Modules |  | Requres tablet
Bug | CUT-550 | interstitial articles on stg (from prod) display image in wrong spot | Nicole Smith | Nicole Smith | Critical | Resolved | Closed | 2012-07-26 15:44 | 2012-08-05 20:33 | Articles
Bug | CUT-704 | Slideshows: Interstitial Ads: Article URL not refreshing when slideshow closed | Kelly Maloni | Kelly Maloni | Critical | Resolved | None | 2012-08-02 00:19 | 2012-08-03 16:41 | Slideshow UX | Sprint 83
Bug | CUT-681 | On STG: Publish time on articles can sometimes be really slow. | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Won't Fix | 2012-08-01 11:23 | 2012-08-03 16:21 | Articles | Sprint 83
Bug | CUT-677 | On STG: Sidekick does not load on page until after several refreshes. | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Won't Fix | 2012-08-01 10:20 | 2012-08-03 16:21 | General Site Issues | Sprint 83
Bug | CUT-692 | enlarge this is enabled but when + is clicked, nothing appears | Kelly Maloni | Sam Lee | Critical | Resolved | Resolved | 2012-08-01 13:54 | 2012-08-03 14:36
Bug | CUT-733 | The CDN host of the primary image is harcoded into the show page's nym:primaryImage property. | Randi Eichenbaum | Georges Labreche | Critical | Resolved | Fixed | 2012-08-03 11:43 | 2012-08-03 11:46 | Show Builder |  | FYI: This fix won't be needed on PROD
Bug | CUT-604 | On STG: IE: Large images are not displaying in on the Homepage. (Lede, Look Book, Goods Module (lede spot), Fashion Shows, Pictures, Giant Image Module). | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Cannot Reproduce | 2012-07-28 17:52 | 2012-08-01 18:25 | Home Page & Modules | Sprint 83 | Was fixed with the 'backward compatibility' button on IE9, but othewise, I cannot reproduce this bug.
Bug | CUT-619 | Flex tags for bottom mobile ads need size adjustments | Kelly Maloni | Kelly Maloni | Critical | Resolved | Fixed | 2012-07-30 01:46 | 2012-08-01 17:38 | Ads
Bug | CUT-439 | Runway Migration: Need to 5x rendition as primary image for shows with hi res runway images | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Fixed | 2012-07-18 17:54 | 2012-08-01 16:50 | Runway Show Opener & Finder | Sprint 83 | I need to either create new content on prod or edit content on prod, similar to CUT-683
Bug | CUT-620 | Add 728x91 to top leaderboard flex tag | Kelly Maloni | Kelly Maloni | Blocker | Resolved | Fixed | 2012-07-30 01:53 | 2012-08-01 16:36 | Ads | Sprint 83
Sub-task | CUT-543 | CUT-492 Enlarge This Is Not Working: Shouldn't have an enlarge span if the orig img doesn't have large enough renditions | Kelly Maloni | Trista Spidaletto | Critical | Resolved | Fixed | 2012-07-26 14:24 | 2012-08-01 13:52 |  | Sprint 83
Bug | CUT-656 | Lede disappears after resizing | Sarah Greis | Sarah Greis | Critical | Resolved | Fixed | 2012-07-31 12:07 | 2012-08-01 12:42 | Splash Pages - All
Bug | CUT-683 | Section Pages: Feeds: Changing the template of an article does not change the rendition that displays in the feed. | Randi Eichenbaum | Randi Eichenbaum | Critical | Resolved | Won't Fix | 2012-08-01 12:08 | 2012-08-01 12:39 | Splash Pages - All |  | Verifying this bug would require me to change articles on prod, which I'm not comfortable doing. I'd need to edit the layouts of articles on author to see if they change in the feeds.
Bug | CUT-337 | Large Vertical: Earlier links should not be appearing under SHOW MORE in left column | Kelly Maloni | Kristen Dudish | Critical | Resolved | Resolved | 2012-07-10 18:40 | 2012-07-31 11:40 | Articles
Bug | CUT-482 | Failure to upload all images when batch uplaoding | Kelly Maloni | Kelly Maloni | Critical | Resolved | Incomplete | 2012-07-23 01:05 | 2012-07-31 11:03 | Image Management | Sprint 83 | Instead of getting an error message, the images never load. I get the "loading" icon and no images are uploaded.
Bug | CUT-623 | Edited rendition file sizes are too large | Steve Motzenbecker | Steve Motzenbecker | Blocker | Resolved | Won't Fix | 2012-07-30 10:42 | 2012-07-31 10:15 | Image Management | Sprint 83
Bug | CUT-622 | HD sizes are showing up double the size they should on the Retina iPads. | Kevin Barnett | Kelly Maloni | Critical | Resolved | Fixed | 2012-07-30 02:03 | 2012-07-30 15:43 | Ads |  | Need iPad
Bug | CUT-511 | Canonical url and og tags need to reference /thecut/ rather than /daily/fashion/ | Kelly Maloni | Kelly Maloni | Blocker | Resolved | Fixed | 2012-07-25 01:54 | 2012-07-30 15:16 | Articles | Sprint 83
Bug | CUT-512 | Word count options in omniture meta data need to change | Kelly Maloni | Kelly Maloni | Major | Resolved | Fixed | 2012-07-25 02:02 | 2012-07-30 15:16 | Articles
Bug | CUT-484 | Runway Show Opener Ads need to change | Kelly Maloni | Kelly Maloni | Blocker | Resolved | Fixed | 2012-07-23 01:26 | 2012-07-28 18:24 | Ads | Sprint 83
Bug | CUT-483 | Changes sizes of ads in premium slideshows | Kelly Maloni | Kelly Maloni | Blocker | Resolved | Fixed | 2012-07-23 01:19 | 2012-07-28 17:46 | Ads | Sprint 83
Bug | CUT-487 | thecut primaryImage component does not add primary_image property breaking endeca (ipad app) | Kelly Maloni | Sam Lee | Critical | Resolved | Fixed | 2012-07-23 13:15 | 2012-07-27 16:38 |  | Sprint 83
Bug | CUT-387 | Cut Party lines entry - image overlaps slideshow button, layout is incorrect. See screenshot | Nicole Smith | Nicole Smith | Critical | Resolved | Won't Fix | 2012-07-13 13:17 | 2012-07-16 13:16 | Articles
Generated at Thu Aug 16 22:58:30 EDT 2012 by Kelly Maloni using JIRA 4.3.4#620-r152668.